## Project Plan
Project Title: RAGSY - CODE TO VISUALIZER
Members: RANJANBABU,YOGESH,SHWETHA,GOUTHAM,AKLIMA BEGUM SARA
Project Plan Started on: 05/01/2026
Tasks | JAN |  |  |  | FEB |  |  |  | MAR |  |  |  | APR |  |  |  | MAY |  |  |  | JUN
| 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
Requirement Analysis & Data Collection
Requirement Review
Database Design & Creation
Database Design Review
Dataflow Diagram
ER Diagram
Authentication Module
Flowchart Engine (AST Parser)
Code Editor & Execution Engine
Flowchart Rendering (React Flow)
Forgot Password & SMS OTP
Code Encryption (AES-256 Fernet)
Admin Dashboard Module
JavaScript Basics Support
Task List & Learning Feature
Dagre Layout & PNG Export Fix
Testing
Implementation / Deployment